## Sheet1
Issue_Type	Time_Spent	Story_point_estimate	Project	Remote_Dev_Approval	Time_Spent_fi	Issue_color	Resolution	Start_date	Request_Type	Request_participants	Resolved	Work_Ratio	Last_Viewed	Watchers	Images	Created	Priority	Flagged	Area_Impacted	Labels	Story_Points	Remaining_Estimate	Original_Estimate_fi	Assignee	Updated	Status	Key	Original_Estimate	Description	Sprint	Rank	CHART_Date_of_First_Response	CHART_Time_in_Status	Story_Points_fi	Time_Tracking	Epic_Name	Epic_Status	Security_Level	Epic_Colour	Epic_Link	Remaining_Estimate_fi	Parent_Link	Summary	Creator	Reporter	Progress_fi	Development	Team	Organizations	Environment	Due_date	Progress	Comment	Votes
Sub-task			BI Reporting Infrastructure							[]		-1	1/3/2019 3:04	1		1/2/2019 10:41	High							dpeela	1/2/2019 10:41	To Do	DAS-373				0|i008d3:											{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"SUBTASK_LINK_SHOULD_BE_USED","message":"To set the parent for a sub-task, use the sub-task link."}}	IICS migration support	{"accountId":"5a6f594de8017b55372b19e1","emailAddress":"jackhaynes@anbtx.com","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/7b41beb46013141c3467e9ef1af7b1fb?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2F7b41beb46013141c3467e9ef1af7b1fb%3	jackhaynes	0	{}					0		0
Task	176400		BI Reporting Infrastructure		176400					[]		-1	1/3/2019 2:54	1		1/2/2019 9:57	Highest					0		dpeela	1/3/2019 1:54	In Progress	DAS-372				0|i008cv:				1w 1d 1h					DAS-362	0	{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"EPIC_LINK_SHOULD_BE_USED","message":"To set an epic as the parent, use the epic link instead"}}	Support and monitoring for 2019	{"accountId":"5a6f594de8017b55372b19e1","emailAddress":"jackhaynes@anbtx.com","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/7b41beb46013141c3467e9ef1af7b1fb?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2F7b41beb46013141c3467e9ef1af7b1fb%3	jackhaynes	176400	{}				12/31/2019 0:00	176400		0
Task	3600		BI Reporting Infrastructure		3600					[]		-1	1/2/2019 8:18	2		12/19/2018 14:57	High					0		dpeela	1/2/2019 3:03	In Progress	DAS-371		Please install JIRA connector into Informatica and develop ETL to support time tracking and invoicing by Miracle		0|i0087b:	2018-12-20T06:10:47.772-0600			1h					DAS-362	0	{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"EPIC_LINK_SHOULD_BE_USED","message":"To set an epic as the parent, use the epic link instead"}}	Please install JIRA connector into Informatica and develop ETL to support time tracking and invoicing by Miracle	{"accountId":"5a6f594de8017b55372b19e1","emailAddress":"jackhaynes@anbtx.com","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/7b41beb46013141c3467e9ef1af7b1fb?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2F7b41beb46013141c3467e9ef1af7b1fb%3	jackhaynes	3600	{}				1/4/2019 0:00	3600	For All project extract getting DTM error unexpectedly and contact Informatica, understand some patch required would like to wait till 7-Jan for IICS sandbox migration to test this back.	0
Epic			BI Reporting Infrastructure							[]		-1		1		12/10/2018 15:33	High							jackhaynes	12/10/2018 15:33	To Do	DAS-366		360 Dashboard_x000D_ / BH Decile_x000D_ / Consider adding hover over to explain what BH Decile means_x000D_ / Remove Cameo Code_x000D_ / Add green Go button to click after choosing customer / Automatically load after selecting customer_x000D_ / Do training_x000D_ / Household_x000D_ / Remove as is_x000D_ / Or Keep and use address as common denominator and refine_x000D_ / Add rows to top table, donâ€™t scroll down_x000D_ / Remove or keep and add training_x000D_ / _x000D_ / _x000D_ / _x000D_ / Portfolio_x000D_ / Increase speed so users have a better experience (I)_x000D_ / Add a key to explain colors used in graphs (I)_x000D_ / Remove Customer by Zip Code (I)_x000D_ / Do training (I)_x000D_ / Drill downs donâ€™t pull accurate information (I)_x000D_ / Y access needs to be clarified (Add data labels) (I)_x000D_ / Deposit Activity shows top ten customers by alphabetical and only by 1 officer (I)_x000D_ / _x000D_ / _x000D_ / _x000D_ / _x000D_ / 360 Dashboard_x000D_ / BH Decile_x000D_ / Consider adding hover over to explain what BH Decile means_x000D_ / Remove Cameo Code_x000D_ / Add green Go button to click after choosing customer / Automatically load after selecting customer_x000D_ / Do training_x000D_ / Household_x000D_ / Remove as is_x000D_ / Or Keep and use address as common denominator and refine_x000D_ / Add rows to top table, donâ€™t scroll down_x000D_ / Remove or keep and add training_x000D_ / _x000D_ / _x000D_ / _x000D_ / Portfolio_x000D_ / Increase speed so users have a better experience (I)_x000D_ / Add a key to explain colors used in graphs (I)_x000D_ / Remove Customer by Zip Code (I)_x000D_ / Do training (I)_x000D_ / Drill downs donâ€™t pull accurate information (I)_x000D_ / Y access needs to be clarified (Add data labels) (I)_x000D_ / Deposit Activity shows top ten customers by alphabetical and only by 1 officer (I)_x000D_ / _x000D_ / _x000D_ / _x000D_ / _x000D_		0|i007wj:					2019 1st Quarter DashBoard Tuning	{"self":"https:\/\/anbtx1875.atlassian.net\/rest\/api\/2\/customFieldOption\/10000","id":"10000","value":"To Do"}		ghx-label-11			{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"TOP_OF_HIERARCHY","message":"An issue at the top of the Portfolio for Jira hierarchy cannot have a parent set."}}	2019 1st Quarter DashBoard Tuning	{"accountId":"5a6f594de8017b55372b19e1","emailAddress":"jackhaynes@anbtx.com","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/7b41beb46013141c3467e9ef1af7b1fb?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2F7b41beb46013141c3467e9ef1af7b1fb%3	jackhaynes	0	{}				12/31/2018 0:00	0		0
Epic		12000	BI Reporting Infrastructure							[]		0	1/2/2019 10:12	1		12/4/2018 15:45	High					28800	28800	jackhaynes	1/2/2019 9:57	To Do	DAS-362	28800			0|i007u3:					ETL, DashBoard and Data Integration Monitoring and Support	{"self":"https:\/\/anbtx1875.atlassian.net\/rest\/api\/2\/customFieldOption\/10000","id":"10000","value":"To Do"}		ghx-label-12		28800	{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"TOP_OF_HIERARCHY","message":"An issue at the top of the Portfolio for Jira hierarchy cannot have a parent set."}}	ETL, API and DB Off-hour support and monitoring	{"accountId":"5a6f594de8017b55372b19e1","emailAddress":"jackhaynes@anbtx.com","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/7b41beb46013141c3467e9ef1af7b1fb?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2F7b41beb46013141c3467e9ef1af7b1fb%3	jackhaynes	0	{}				12/31/2019 0:00	0		0
Epic		19000	BI Reporting Infrastructure							[]		-1		1		11/29/2018 8:40	Highest							jackhaynes	12/28/2018 10:28	In Progress	DAS-352				0|i00505:					WIG 2019	{"self":"https:\/\/anbtx1875.atlassian.net\/rest\/api\/2\/customFieldOption\/10000","id":"10000","value":"To Do"}		ghx-label-12			{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"TOP_OF_HIERARCHY","message":"An issue at the top of the Portfolio for Jira hierarchy cannot have a parent set."}}	Grow the number of "A" profitable relationships from X to Y by 10/31/2019	{"accountId":"5a6f593a46cb74525803180f","emailAddress":"jakerandolph@anbtx.com","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/b4cd9c646a3195b45891c9caf241a0c6?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2Fb4cd9c646a3195b45891c9caf241a0c6	jakerandolph	0	{}				1/31/2019 0:00	0		0
Epic			BI Reporting Infrastructure							[]		-1		1		11/1/2018 10:59	Medium							jackhaynes	11/16/2018 13:13	To Do	DAS-300				0|i006df:					Integration	{"self":"https:\/\/anbtx1875.atlassian.net\/rest\/api\/2\/customFieldOption\/10000","id":"10000","value":"To Do"}		ghx-label-5			{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"TOP_OF_HIERARCHY","message":"An issue at the top of the Portfolio for Jira hierarchy cannot have a parent set."}}	Integration	{"accountId":"5a6f593a46cb74525803180f","emailAddress":"jakerandolph@anbtx.com","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/b4cd9c646a3195b45891c9caf241a0c6?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2Fb4cd9c646a3195b45891c9caf241a0c6	jakerandolph	0	{}					0		0
Epic			BI Reporting Infrastructure							[]		-1		1		11/1/2018 10:51	Medium							jackhaynes	11/30/2018 13:17	To Do	DAS-299				0|i0050d:					Automation	{"self":"https:\/\/anbtx1875.atlassian.net\/rest\/api\/2\/customFieldOption\/10000","id":"10000","value":"To Do"}		ghx-label-2			{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"TOP_OF_HIERARCHY","message":"An issue at the top of the Portfolio for Jira hierarchy cannot have a parent set."}}	Automation	{"accountId":"5a6f593a46cb74525803180f","emailAddress":"jakerandolph@anbtx.com","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/b4cd9c646a3195b45891c9caf241a0c6?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2Fb4cd9c646a3195b45891c9caf241a0c6	jakerandolph	0	{}					0		0
Epic			BI Reporting Infrastructure							[]		-1	12/5/2018 5:14	1		11/1/2018 10:48	Medium							jackhaynes	12/5/2018 5:14	To Do	DAS-298				0|i0050p:					Data Warehouse	{"self":"https:\/\/anbtx1875.atlassian.net\/rest\/api\/2\/customFieldOption\/10000","id":"10000","value":"To Do"}		ghx-label-14			{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"TOP_OF_HIERARCHY","message":"An issue at the top of the Portfolio for Jira hierarchy cannot have a parent set."}}	Data Warehouse	{"accountId":"5a6f593a46cb74525803180f","emailAddress":"jakerandolph@anbtx.com","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/b4cd9c646a3195b45891c9caf241a0c6?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2Fb4cd9c646a3195b45891c9caf241a0c6	jakerandolph	0	{}					0		0
Epic			BI Reporting Infrastructure							[]		-1		1		10/17/2018 21:10	Medium							jackhaynes	11/27/2018 11:39	To Do	DAS-236				0|i005g3:					Release	{"self":"https:\/\/anbtx1875.atlassian.net\/rest\/api\/2\/customFieldOption\/10000","id":"10000","value":"To Do"}		ghx-label-6			{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"TOP_OF_HIERARCHY","message":"An issue at the top of the Portfolio for Jira hierarchy cannot have a parent set."}}	Release	{"accountId":"5a6f593a46cb74525803180f","emailAddress":"jakerandolph@anbtx.com","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/b4cd9c646a3195b45891c9caf241a0c6?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2Fb4cd9c646a3195b45891c9caf241a0c6	jakerandolph	0	{}					0		0
Epic			BI Reporting Infrastructure							[]		-1		1		10/11/2018 14:31	Medium							jackhaynes	11/29/2018 9:22	To Do	DAS-229				0|i006dj:					Innovation Ideas	{"self":"https:\/\/anbtx1875.atlassian.net\/rest\/api\/2\/customFieldOption\/10000","id":"10000","value":"To Do"}		ghx-label-7			{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"TOP_OF_HIERARCHY","message":"An issue at the top of the Portfolio for Jira hierarchy cannot have a parent set."}}	Innovation Ideas	{"accountId":"5a6f593a46cb74525803180f","emailAddress":"jakerandolph@anbtx.com","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/b4cd9c646a3195b45891c9caf241a0c6?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2Fb4cd9c646a3195b45891c9caf241a0c6	jakerandolph	0	{}					0		0
Epic			BI Reporting Infrastructure		374400					[]		-1		1		10/4/2018 8:46	Medium							jackhaynes	12/5/2018 16:56	In Progress	DAS-199				0|i0050l:					Data & Code Management	{"self":"https:\/\/anbtx1875.atlassian.net\/rest\/api\/2\/customFieldOption\/10000","id":"10000","value":"To Do"}		ghx-label-10		0	{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"TOP_OF_HIERARCHY","message":"An issue at the top of the Portfolio for Jira hierarchy cannot have a parent set."}}	Code Management	{"accountId":"5a6f593a46cb74525803180f","emailAddress":"jakerandolph@anbtx.com","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/b4cd9c646a3195b45891c9caf241a0c6?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2Fb4cd9c646a3195b45891c9caf241a0c6	jakerandolph	374400	{}					0		0
Task			Data as a Service (DAAS)							[]		-1	10/16/2018 9:07	1		9/27/2018 13:54	Medium								9/27/2018 14:43	To Do	DAAS-67				0|i004wl:											{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"EPIC_LINK_SHOULD_BE_USED","message":"To set an epic as the parent, use the epic link instead"}}	Vendor notification and 1-3 definition	{"accountId":"5a6f594de8017b55372b19e1","emailAddress":"jackhaynes@anbtx.com","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/7b41beb46013141c3467e9ef1af7b1fb?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2F7b41beb46013141c3467e9ef1af7b1fb%3	jackhaynes	0	{}					0		0
Task			Data as a Service (DAAS)				Done			[]	9/27/2018 14:44	-1		1		9/27/2018 13:53	High							jackhaynes	9/27/2018 14:45	Done	DAAS-66				0|i004wd:		10000_*:*_1_*:*_3075426_*|*_10001_*:*_1_*:*_0									{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"EPIC_LINK_SHOULD_BE_USED","message":"To set an epic as the parent, use the epic link instead"}}	Get profitability deck from Greg	{"accountId":"5a6f594de8017b55372b19e1","emailAddress":"jackhaynes@anbtx.com","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/7b41beb46013141c3467e9ef1af7b1fb?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2F7b41beb46013141c3467e9ef1af7b1fb%3	jackhaynes	0	{}					0	I added deck to the profitability definition on SharePoint_x000D_ / _x000D_ / Deck is at https://anbtx.sharepoint.com/:p:/s/ANBTX-SharePoint/Information%20Technology/DWReport/Eb8ZKNWj_2JHpoHLZCfVO0IBD4FTlObtb-g5zEMNRnkpCA_x000D_ / _x000D_ / I added deck to the profitability definition on SharePoint_x000D_ / _x000D_ / Deck is at https://anbtx.sharepoint.com/:p:/s/ANBTX-SharePoint/Information%20Technology/DWReport/Eb8ZKNWj_2JHpoHLZCfVO0IBD4FTlObtb-g5zEMNRnkpCA_x000D_ / _x000D_	0
Story			Data as a Service (DAAS)							[]		-1		1		9/7/2018 13:54	Medium								9/7/2018 13:55	To Do	DAAS-64			["com.atlassian.greenhopper.service.sprint.Sprint@243c4a9f[id=37,rapidViewId=30,state=FUTURE,name=DSD Sprint 2,goal=<null>,startDate=<null>,endDate=<null>,completeDate=<null>,sequence=37]"]	0|i004il:									DAAS-9		{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"EPIC_LINK_SHOULD_BE_USED","message":"To set an epic as the parent, use the epic link instead"}}	Develop governance execution plan	{"accountId":"5a6b8eaf23d8016cc6b5df83","emailAddress":"gailmason@anbtx.com","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/cbc057545e98c7476f25007d68f43127?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2Fcbc057545e98c7476f25007d68f43127%3F	admin	0	{}					0		0
Story			Data as a Service (DAAS)							[]		-1		1		9/7/2018 13:50	Medium								9/7/2018 13:53	To Do	DAAS-63			["com.atlassian.greenhopper.service.sprint.Sprint@2390f74c[id=37,rapidViewId=30,state=FUTURE,name=DSD Sprint 2,goal=<null>,startDate=<null>,endDate=<null>,completeDate=<null>,sequence=37]"]	0|i004id:									DAAS-9		{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"EPIC_LINK_SHOULD_BE_USED","message":"To set an epic as the parent, use the epic link instead"}}	Formalize data governance strategy	{"accountId":"5a6b8eaf23d8016cc6b5df83","emailAddress":"gailmason@anbtx.com","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/cbc057545e98c7476f25007d68f43127?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2Fcbc057545e98c7476f25007d68f43127%3F	admin	0	{}					0		0
Story			Newgen CLOS Implementation							[]		-1		1		12/28/2018 9:10	Medium							sumit_kumar	1/2/2019 7:27	To Do	NCI-329				0|i008bf:											{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"EPIC_LINK_SHOULD_BE_USED","message":"To set an epic as the parent, use the epic link instead"}}	Incorporation of CC Email address for Auto emails going out from Online system	{"accountId":"5b72e8fdfdc47d05bd1d7f70","emailAddress":"himanshu.jain@newgen.co.in","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/c45221d9994d6a80ecb2a830c8e5b844?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2Fc45221d9994d6a80ecb2a830c8e5	himanshu.jain	0	{}					0		0
Sub-task			Newgen CLOS Implementation							[]		-1		1		12/28/2018 9:10	Highest							vkhilnani	12/28/2018 9:10	To Do	NCI-328		Need resolution from Experian to get credit profile working in UAT environment.		0|i008bj:											{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"SUBTASK_LINK_SHOULD_BE_USED","message":"To set the parent for a sub-task, use the sub-task link."}}	Blocked - Need resolution from Experian	{"accountId":"5b85726bd043fc2a665e6972","emailAddress":"vkhilnani@miraclesoft.com","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/08edf15cf96125db149dfef172a4707a?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2F08edf15cf96125db149dfef172a47	vkhilnani	0	{}				12/30/2018 0:00	0		0
Task			Newgen CLOS Implementation							[]		-1		1		12/28/2018 9:08	Medium							brunoskerianz	12/28/2018 9:11	To Do	NCI-327		Details to be provided by Bruno for CC (Internal email address) to be communicated by bruno , that are to be added in CC for each auto email going to customer by system		0|i008bb:											{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"EPIC_LINK_SHOULD_BE_USED","message":"To set an epic as the parent, use the epic link instead"}}	(Online) For applications initiated on online / mobile, CC Email address to be confirmed by Bruno after discussion with Denise	{"accountId":"5b72e8fdfdc47d05bd1d7f70","emailAddress":"himanshu.jain@newgen.co.in","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/c45221d9994d6a80ecb2a830c8e5b844?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2Fc45221d9994d6a80ecb2a830c8e5	himanshu.jain	0	{}					0		0
Task			Newgen CLOS Implementation							[]		-1		1		12/27/2018 11:25	Highest							brunoskerianz	12/27/2018 11:25	To Do	NCI-326		Bruno to reach out to Melissa to see what these are supposed to be for the consumer loans.		0|i008b3:											{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"EPIC_LINK_SHOULD_BE_USED","message":"To set an epic as the parent, use the epic link instead"}}	Get GL codes for booking loans	{"accountId":"5a6f594de8017b55372b19e1","emailAddress":"jackhaynes@anbtx.com","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/7b41beb46013141c3467e9ef1af7b1fb?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2F7b41beb46013141c3467e9ef1af7b1fb%3	jackhaynes	0	{}				12/28/2018 0:00	0		0
Task			Newgen CLOS Implementation							[]		-1		1		12/27/2018 11:24	Medium							Dchauhan	12/27/2018 11:24	To Do	NCI-325		NewGen will tell us whether they want weekly FTP or weekly API to get the latest officer codes to userid from AD. Userid can be either jhaynes@anbtx.com or jackhaynes@anbtx.com and NewGen needs to tell us which they will use._x000D_ / _x000D_ / Initially will ask that the business send over soem sampels of 5-6 to get newGen team working on development.		0|i008av:									NCI-278		{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"EPIC_LINK_SHOULD_BE_USED","message":"To set an epic as the parent, use the epic link instead"}}	Create officer code feed/api to AD userid used in newGen	{"accountId":"5a6f594de8017b55372b19e1","emailAddress":"jackhaynes@anbtx.com","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/7b41beb46013141c3467e9ef1af7b1fb?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2F7b41beb46013141c3467e9ef1af7b1fb%3	jackhaynes	0	{}				1/11/2019 0:00	0		0
Task			Newgen CLOS Implementation							[]		-1		1		12/27/2018 11:19	Medium							Dchauhan	12/27/2018 11:19	To Do	NCI-324		Need an API that will enable NewGen to push supporting loan documentation (assume in PDF but need confirmed by NewGen) to OnBase via MTS then provide docopop link back to Newgen application so documents are maintained/versioned in one place.		0|i008an:									NCI-278		{"hasEpicLinkFieldDependency":false,"showField":false,"nonEditableReason":{"reason":"EPIC_LINK_SHOULD_BE_USED","message":"To set an epic as the parent, use the epic link instead"}}	Document OnBase API to support add supporting loan documents to OnBase then provide docpop link	{"accountId":"5a6f594de8017b55372b19e1","emailAddress":"jackhaynes@anbtx.com","avatarUrls":{"48x48":"https:\/\/avatar-cdn.atlassian.com\/7b41beb46013141c3467e9ef1af7b1fb?s=48&d=https%3A%2F%2Fsecure.gravatar.com%2Favatar%2F7b41beb46013141c3467e9ef1af7b1fb%3	jackhaynes	0	{}				1/14/2019 0:00	0		0